## Overview
Booking system: flows & features
How to use
Flows: one row per task to build. Work through it by Phase (1 -> 4).
Features: every requirement we agreed, with the flows that cover it.
Edit only the yellow cells: Status (dropdown) and Notes.
Status values: To do, In progress, Done, Blocked. Progress below updates itself.
Schema, Permissions and Insert audit tabs are reference, not tasks.
Status cell looks like this: | To do
Progress by area
Area | Tasks | Done | In progress | % done
Foundation | 3 | 0 | 0 | 0%
Owner setup | 5 | 0 | 0 | 0%
Barber setup | 3 | 0 | 0 | 0%
Shifts & availability | 4 | 0 | 0 | 0%
Customer booking | 6 | 0 | 0 | 0%
Barber appointments | 7 | 0 | 0 | 0%
Emergency | 2 | 0 | 0 | 0%
Payments | 2 | 0 | 0 | 0%
In-store sales | 3 | 0 | 0 | 0%
Accounting | 7 | 0 | 0 | 0%
Rent | 4 | 0 | 0 | 0%
Scheduled jobs | 2 | 0 | 0 | 0%
Notifications | 2 | 0 | 0 | 0%
All flows | 50 | 0 | 0 | 0%
Features | 31 | 0 | 0 | 0%

## Flows
ID | Area | Phase | Flow / task | Actor | Trigger | How it flows | Tables touched | Rules & edge cases | Depends on | Status | Notes
FND-01 | Foundation | 1 - Foundation | Write schema + migration | Dev | Start of build | 1. Add enums: payment_method, appointment_source, appointment_status, appointment_event_kind, appointment_payment_kind, rent_period, rent_status, rent_paid_via, barber_ledger_kind. 2. Create tables: locations, barbers, services, barber_shifts, barber_terms, rent_charges, appointments, appointment_services, appointment_events, appointment_payments, in_store_sales, barber_ledger. 3. NO changes to existing tables, columns or enums: in-store sales are marked by the in_store_sales side table; barber access comes from barbers.user_id, not user_role. Rollback: drizzle/rollback/0006_booking.down.sql. 4. Hand-written SQL: CREATE EXTENSION btree_gist; no-overlap EXCLUDE constraints on barber_shifts and appointments; CHECK constraints, including: a booked / completed / no_show appointment must have confirmed_at, and an online booking must have booking_fee > 0. | All | Verify PGlite (local dev) can load btree_gist before relying on it. Existing orders get channel = 'online' and satisfy the new CHECK, so no existing data changes. | - | To do
FND-02 | Foundation | 1 - Foundation | Barber role & login | Barber | Barber opens /admin/login | 1. Barber enters email -> same email-OTP flow the owner uses. 2. The admin lookup becomes a staff lookup: role admin, OR a user linked from an active barbers row. 3. Session carries role + linked barber_id. 4. Admin layout shows only the barber menu for role barber. | users, barbers, sessions, otp_codes | A barber login with no linked barbers row sees 'ask the owner to link your profile'. Role is re-checked at code verification, as it is for admins today. | FND-01 | To do
FND-03 | Foundation | 1 - Foundation | Permission guards | Dev | Every server function | 1. requireOwner() on owner-only functions: products, stock, prices, settings, locations, terms, rent, payouts, adjustments. 2. requireStaff() returns { userId, role, barberId }. 3. Barber functions always filter by the session's barberId; a barber_id sent from the browser is never trusted. | - | Test: barber A cannot read or change barber B's appointments, services, shifts or ledger by guessing ids. | FND-02 | To do
OWN-01 | Owner setup | 1 - Foundation | Manage locations | Owner | New branch / change | 1. Create: slug, names MN/EN, address, phone, map link. 2. Edit any field. 3. Deactivate (is_active = false) instead of deleting. | locations | Deactivated locations disappear from online booking; existing appointments there stay valid. Delete is blocked while any appointment references it. | FND-03 | To do
OWN-02 | Owner setup | 1 - Foundation | Create barber & grant login | Owner | New barber joins | 1. Create barbers row: name, slug, phone (required), photo, bio, booking fee, buffer. 2. Grant login: create or promote a users row with role barber and link barbers.user_id. 3. Set their terms (OWN-03). | barbers, users, barber_terms | Phone is required: customers see it on every confirmation. A barber can exist without a login; the owner then manages them. | FND-02 | To do
OWN-03 | Owner setup | 3 - Money | Set / change barber terms | Owner (agreed with barber) | Deal agreed or changed | 1. Enter service cut %, product commission %, rent amount, rent period, rent start date, effective-from date. 2. Saved as a NEW row; the old row is never edited. 3. Ledger rows and rent charges created after effective-from use the new terms. | barber_terms | Percentages stored as basis points 0-10000 (3000 = 30%). Barbers can view their terms but never edit them. | OWN-02 | To do
OWN-04 | Owner setup | 4 - Extras | Deactivate barber | Owner | Barber leaves | 1. Set is_active = false; hidden from online booking. 2. Revoke login (unlink barbers.user_id, sessions deleted). 3. Owner sees their future appointments to reassign or cancel by phone. | barbers, users, sessions, appointments | A barber with history can't be deleted (restrict FKs). Ledger balance and unpaid rent stay visible until settled. | OWN-02 | To do
OWN-05 | Owner setup | 2 - Booking core | Owner who also cuts hair | Owner | - | 1. Link the owner's admin user to a barbers row. 2. They get owner screens plus their own barber screens. | users, barbers | Role stays admin; barber scoping comes from the linked barber_id, not the role. | FND-03 | To do
BAR-01 | Barber setup | 2 - Booking core | Edit own profile | Barber | Anytime | 1. Edit name, bio, photo, phone, booking fee, buffer minutes. | barbers | Fee and buffer changes apply to NEW bookings only; existing appointments keep their frozen values. Fee 0 = no online booking; customers see 'Call to book'. | FND-03 | To do
BAR-02 | Barber setup | 2 - Booking core | Create a service | Barber | Anytime | 1. Pick a location. 2. Enter name EN (required), name MN (optional), description, price, duration. 3. Save -> bookable wherever the barber has shifts at that location. | services | The same service at another branch is a new row with its own price ('copy to another location' helper). Duration > 0, price >= 0. The barber decides everything; the owner doesn't define service types. | BAR-01 | To do
BAR-03 | Barber setup | 2 - Booking core | Edit / deactivate a service | Barber | Price or offer changes | 1. Change price, duration or name, or set inactive. | services | Past and upcoming appointments keep their frozen name, price and duration. Inactive services only disappear from new bookings. | BAR-02 | To do
SHF-01 | Shifts & availability | 2 - Booking core | Plan shifts | Barber | Whenever they like | 1. Add a shift: location, date, from-to. Any day, any hours, no fixed weekly pattern. 2. Several shifts a day are fine (morning at A, afternoon at B). 3. Online booking opens inside these windows only. | barber_shifts | The database refuses overlapping shifts for the same barber (they can't be in two places at once). ends_at must be after starts_at. | BAR-02 | To do
SHF-02 | Shifts & availability | 4 - Extras | Copy / repeat shifts | Barber | Planning ahead | 1. 'Copy last week' or 'repeat this shift for N weeks'. 2. Creates ordinary shift rows, each editable on its own. | barber_shifts | Copies that would overlap existing shifts are skipped and listed, not failed as a batch. | SHF-01 | To do
SHF-03 | Shifts & availability | 2 - Booking core | Edit / remove a shift that has bookings | Barber | Plans change | 1. Shorten or delete the shift. 2. Bookings inside it are NOT cancelled; they simply become outside-schedule (overtime) bookings. 3. UI warns: 'N bookings are now outside your schedule'. | barber_shifts, appointments | Appointments never point at shifts, so nothing needs cleaning up. | SHF-01 | To do
SHF-04 | Shifts & availability | 2 - Booking core | Availability (free slots) | System | Customer opens booking | 1. Take the barber's shifts at that location for the day. 2. Subtract every active appointment's [starts_at, blocked_until) at ANY location. 3. Offer start times (15-min grid) where total service duration + buffer fits entirely inside what's left of a shift. | barber_shifts, appointments, services, barbers | Computed live, never stored. So: a booking inside a shift automatically takes those slots; an overtime booking outside the shift takes nothing from it; if a shift is later extended over an overtime booking, that time just shows as taken. Active = not cancelled; pending holds count, so nobody can take a slot someone else is paying for. | SHF-01 | To do
CUS-01 | Customer booking | 2 - Booking core | Browse & pick | Customer | Opens booking page | 1. Pick location. 2. See barbers with active services and upcoming shifts there. 3. Pick barber -> their services at that location (one or more). 4. Pick day -> available start times (SHF-04). 5. A barber with no booking fee shows 'Call to book' + their phone instead of times. | (read only) | Browsing never writes anything. Online booking always needs a fee, so a no-fee barber is phone-only. Services from different locations can't be combined. | SHF-04 | To do
CUS-02 | Customer booking | 2 - Booking core | Hold the slot while the customer pays | Customer | Picks a time and presses Pay | 1. Enter name, phone and email (all required online), note. 2. Server re-checks availability; prices come from services; fee = min(barber fee, total). 3. ONE transaction: insert a HOLD (appointment status pending + its lines, expires_at = invoice lifetime) and a pending fee payment row; create the QPay invoice. 4. Nothing else is written: no event, no email, no ledger, no attempts log. | appointments (pending), appointment_services, appointment_payments (pending) | The hold is the ONLY thing written before money, and only because two customers must never pay for the same slot: the overlap constraint needs a row to check against. It is temporary: an unpaid hold is DELETED (CUS-05), never archived. Abuse limit: one active hold per phone, a few per IP, counted from live holds. | CUS-01 | To do
CUS-03 | Customer booking | 3 - Money | Fee paid -> booking exists | Customer | QPay confirms the fee | 1. Callback or polling confirms payment. 2. ONE transaction: payment paid, hold becomes booked, confirmed_at, event 'created', ledger rows (ACC-01). 3. After commit: confirmation email (NTF-02). | appointment_payments, appointments, appointment_events, barber_ledger | This is the moment the booking really exists: every durable record is written here, behind the money. A paid fee is the only way an online booking is confirmed. Duplicate callbacks / sweep race can't double-confirm or double-email (fee-paid-once index, confirmation_sent_at). No refunds, ever. | CUS-02 | To do
CUS-04 | Customer booking | 2 - Booking core | Booking status page | Customer | After CUS-02 | 1. Page via access-token link, showing the current state: - holding: 'Pay the booking fee to confirm' + QPay links, countdown. - confirmed: date/time, location + map, barber name + PHONE, services, total, fee paid, due at the shop, 'call your barber to reschedule or cancel'. - hold gone: 'This time wasn't booked' + barber phone. | (read only) | Only says 'Confirmed' when status is booked. A deleted hold simply reads as 'not booked'. Customers can't cancel or reschedule online. Access token stored hashed. | CUS-02 | To do
CUS-05 | Customer booking | 3 - Money | Unpaid hold is deleted | System | Scheduled sweep | 1. For each hold past expires_at: ask QPay one last time whether the fee was paid. 2. Paid -> run CUS-03 (booked + email). 3. Not paid -> cancel the invoice at QPay; once QPay confirms the cancel, DELETE the pending payment row and the hold (its lines go with it). | appointments, appointment_services, appointment_payments | Delete only after QPay confirms the cancel, so a payment can never land with nothing to match it; if the cancel fails, keep the hold and retry next sweep. Unpaid attempts leave no trace. The old 'fee paid after expiry' edge case is gone: the invoice is dead before the hold is. | CUS-03, JOB-01 | To do
CUS-06 | Customer booking | 2 - Booking core | Customer wants to change or cancel | Customer -> Barber | Customer calls | 1. Customer calls the barber's number from the confirmation. 2. Barber does APT-03 (reschedule) or APT-05 (cancel). | - | No customer self-service; only the barber changes bookings. | CUS-04 | To do
APT-01 | Barber appointments | 2 - Booking core | Barber's calendar | Barber | Daily use | 1. Day / week view across all their locations. 2. Shifts as background, appointments on top, overtime bookings marked, needs-reschedule items highlighted. 3. Open an appointment -> customer name + phone, services, fee paid, balance due, history. | appointments, barber_shifts, appointment_events | Overtime = an appointment not fully inside any shift; computed for display, never stored. | SHF-04 | To do
APT-02 | Barber appointments | 2 - Booking core | Barber creates phone / in-person booking | Barber | Customer calls or is at the shop | 1. Pick location, services (their own at that location), date and time: ANY time, inside or outside shifts. 2. Enter customer name + phone (email optional). 3. Saved as source barber, booking_fee 0, status booked, confirmed_via = barber, confirmed_by = barber, no hold, event 'created'. 4. If an email was given, send the confirmation email (NTF-02). | appointments, appointment_services, appointment_events | Creating it IS the barber's confirmation, so it's confirmed immediately. The one booking insert with no money in front of it, on purpose: a logged-in barber vouches for the customer. Inside a shift -> it automatically takes those online slots (SHF-04). Outside -> overtime, the planned schedule is untouched. Only overlap with the barber's own bookings is refused. Full price is paid at the shop. | APT-01 | To do
APT-03 | Barber appointments | 2 - Booking core | Reschedule | Barber (only) | Customer asked or barber needs to | 1. Pick a new date/time: any time, shifts optional; a different location only if the same services exist there (lines remapped). 2. Update starts_at, ends_at, blocked_until on the SAME row (buffer from the appointment's frozen value). 3. Event 'rescheduled' with from -> to. 4. Clear needs_reschedule_at if set. 5. Email the customer if there's an email. | appointments, appointment_events, appointment_services | The booking fee carries over automatically (same row, same payments). Overlap is still enforced. | APT-01 | To do
APT-04 | Barber appointments | 3 - Money | Change services on an appointment | Barber | Customer adds / drops a service | 1. Add or remove lines (barber's services at that location). 2. Recompute total, ends_at, blocked_until. 3. Event 'updated'. | appointment_services, appointments | booking_fee must stay <= total. Overlap re-checked if it gets longer. Not allowed once completed. | APT-01 | To do
APT-05 | Barber appointments | 2 - Booking core | Cancel | Barber (only) | Customer asked; barber confirms | 1. Status cancelled, reason note, event 'cancelled'. 2. Slot frees. | appointments, appointment_events | Booking fee is kept; no refunds. Customers can't cancel themselves. | APT-01 | To do
APT-06 | Barber appointments | 2 - Booking core | No-show | Barber | Customer never came | 1. Mark no_show, event. | appointments, appointment_events | Fee kept. Only possible after starts_at. | APT-01 | To do
APT-07 | Barber appointments | 3 - Money | Checkout & complete | Barber | Service finished | 1. Screen shows total, fee already paid, and what's left to pay. 2. Add payments in any mix: QPay (QR on the barber's screen), cash, POS, bank transfer. 3. Cash / POS / transfer are saved as paid on entry; QPay waits for confirmation. 4. When paid total = appointment total exactly -> Complete -> completed, event. 5. Ledger rows per payment (ACC-01). | appointment_payments, appointments, barber_ledger, appointment_events | Can't complete until balanced, can't overpay. No tips: extra money is the barber's and never entered. A wrong manual entry is fixed by an owner adjustment (ACC-06), not an edit. | APT-01, ACC-01 | To do
EMG-01 | Emergency | 3 - Money | Emergency: clear a period | Barber | Sick / urgent | 1. Barber picks a period (today, or Tue-Thu). 2. Shifts in that period are removed or shortened -> no new online bookings. 3. Every active appointment in the period gets needs_reschedule_at + event 'flagged'. 4. Appointments keep their original time until handled. | barber_shifts, appointments, appointment_events | Nothing is auto-cancelled; every customer is contacted personally. Flagged bookings still hold their old times, so nothing new lands there. | APT-01 | To do
EMG-02 | Emergency | 3 - Money | Emergency call list | Barber | After EMG-01 | 1. List of flagged appointments: customer name, phone (tap to call), email, services, original time, fee paid. 2. For each: call -> agree a new day -> APT-03 (flag cleared, fee carries over), OR customer declines -> APT-05. 3. The list stays until every item is handled. | appointments, appointment_events | Optional button: email all flagged customers a short notice with the barber's phone, for anyone who doesn't pick up. | EMG-01 | To do
PAY-01 | Payments | 3 - Money | QPay invoice from the admin panel | Barber | Balance or product sale | 1. Create an invoice for the amount -> QR + bank links on the barber's screen. 2. Customer scans with their phone. 3. Polling / callback marks it paid. | appointment_payments, payments | Reuses the existing QPay client and its poll throttling (last_checked_at). | FND-01 | To do
PAY-02 | Payments | 3 - Money | Manual payment entry (cash / POS / transfer) | Barber | Customer pays | 1. Choose method and amount. 2. Saved as paid, received_by = barber. 3. Ledger rows written in the same transaction. | appointment_payments, payments, barber_ledger | Amount can't exceed what's left to pay. | FND-01 | To do
STO-01 | In-store sales | 3 - Money | Build a product sale | Barber | Customer wants a product | 1. Build the sale on screen: product / variant + qty; price from the variant, not editable. 2. Stock checked live. 3. Nothing is saved yet; the order is written together with its first payment (STO-02). | (nothing until STO-02) | Barbers can never edit stock, prices or products. An abandoned sale leaves nothing behind. | FND-03 | To do
STO-02 | In-store sales | 3 - Money | Take payment -> order saved, stock deducted | Barber | Customer pays | 1. Cash / POS / transfer: ONE transaction inserts the order + items + in_store_sales row (barber, location) + the paid payment (provider = the method). Address snapshot = the shop location; contact phone = the customer's. 2. QPay: insert order + pending payment as a hold and show the QR. 3. Split payments: the first payment creates the order, the rest attach to it. 4. When payments add up to the total -> existing settlement: stock deducted with the oversell guard, inventory_ledger written, status paid -> delivered. | orders, order_items, payments, product_variants, inventory_ledger | Settlement stays the only way stock changes. An unpaid QPay in-store order is DELETED by the sweep after QPay confirms the cancel (same rule as booking holds). A partly paid order stays: money was taken. Order state machine needs paid -> delivered for in_store. | STO-01 | To do
STO-03 | In-store sales | 3 - Money | Product commission | System | Each paid payment on an in-store order | 1. product_commission = amount x the barber's product commission % (terms in force). 2. If cash: also cash_collected -amount. | barber_ledger | Online orders never create commission. The rate is frozen on the row. | STO-02, ACC-01 | To do
ACC-01 | Accounting | 3 - Money | Ledger rows on appointment payments | System | A payment becomes paid | 1. service_share = amount - shop cut (terms in force; rate frozen on the row). 2. If cash: also cash_collected -amount (the barber holds that cash and owes it back). 3. Same transaction as marking the payment paid. | barber_ledger, barber_terms | QPay / POS / transfer land in the shop's main account; cash stays with the barber. Integer mungu; shop cut rounded down. Unique (payment, kind) stops duplicates. | OWN-03 | To do
ACC-02 | Accounting | 3 - Money | Barber earnings screen | Barber | Anytime | 1. Pick a date range. 2. Totals: services earned, product commission, cash held, rent deducted, payouts, hand-ins. 3. Current balance: + shop owes you / - you owe the shop. 4. Line list linked to appointments and orders; rent charges due. | barber_ledger, rent_charges | Read-only for barbers. | ACC-01 | To do
ACC-03 | Accounting | 3 - Money | Owner: all barber balances | Owner | Anytime | 1. One row per barber: balance, cash outstanding, rent due / overdue. 2. Open any barber's ledger. | barber_ledger, rent_charges | - | ACC-01 | To do
ACC-04 | Accounting | 3 - Money | Cash hand-in | Owner confirms | Barber pays cash back to the main account | 1. Owner records settlement +amount with a note. | barber_ledger | Only the owner can confirm, so a barber can't clear their own debt. | ACC-01 | To do
ACC-05 | Accounting | 3 - Money | Payout with automatic rent deduction | Owner | Paying the barber | 1. System shows balance B (what the shop owes) and due rent charges. 2. Due rent is deducted automatically, oldest first, while it fits in B: rent_deduction -amount per charge; the charge is marked paid (paid_via payout). 3. What's left is paid out -> payout -amount. | barber_ledger, rent_charges | If B <= 0 (the barber owes the shop, e.g. cash), there's no payout and rent stays due. A rent charge is deducted whole or not at all. | ACC-01, RNT-02 | To do
ACC-06 | Accounting | 4 - Extras | Adjustment | Owner | Correction needed | 1. +/- amount, note required. | barber_ledger | The ledger is append-only; mistakes are corrected with a counter-entry, never edited. | ACC-01 | To do
ACC-07 | Accounting | 3 - Money | Terms change mid-period | System | Owner saves new terms | 1. Only rows created after effective-from use the new %. | barber_terms, barber_ledger | Old rows keep their frozen rate; history never changes. | OWN-03 | To do
RNT-01 | Rent | 3 - Money | Rent agreement | Owner + barber | Agreed between them | 1. Owner enters amount, period (weekly / every 2 weeks / monthly) and start date in the barber's terms. | barber_terms | Only those three periods. Rent 0 = commission-only barber. Rent and commission can both apply. | OWN-03 | To do
RNT-02 | Rent | 3 - Money | Generate rent charges | System | Daily sweep | 1. For each barber with rent: due dates = start date + n x period. 2. When a due date arrives, insert a rent_charges row with the amount frozen. | rent_charges | Unique (barber, due_on): running twice never charges twice. Changed terms only affect charges created afterwards. Monthly starting on the 29th-31st falls on the month's last day. | RNT-01, JOB-02 | To do
RNT-03 | Rent | 3 - Money | Owner confirms direct rent payment | Owner | Barber paid rent directly | 1. Mark the charge paid (paid_via direct), confirmed_by, note; or waive it. | rent_charges | Only the owner confirms. No ledger row: the barber paid from their own pocket. | RNT-02 | To do
RNT-04 | Rent | 4 - Extras | Overdue rent | Owner / Barber | Anytime | 1. Owner: list of charges past due_on. 2. Barber: own due rent on the earnings screen. | rent_charges | The next payout deducts it automatically (ACC-05). | RNT-02 | To do
JOB-01 | Scheduled jobs | 3 - Money | Sweep: delete unpaid holds | System | Existing reconcile sweep | 1. Booking holds (CUS-05) and unpaid QPay in-store orders (STO-02) past expiry: final QPay check -> confirm if paid, else cancel invoice and delete. | appointments, appointment_payments, orders, payments | Added to the existing sweep, reusing its overlap protection. Delete only after QPay confirms the cancel. | CUS-02, STO-02 | To do
JOB-02 | Scheduled jobs | 3 - Money | Sweep: rent charges | System | Daily | 1. Runs RNT-02. | rent_charges | Safe to re-run. | RNT-01 | To do
NTF-01 | Notifications | 4 - Extras | Change emails (reschedule / cancel / flag) | System | Rescheduled / cancelled / flagged | 1. Only when the customer gave an email. 2. Sent via Resend in the same email shell as receipts; always includes the barber's phone. | - | Best-effort: a failed email never blocks the booking change. SMS is out of scope. | NTF-02 | To do
NTF-02 | Notifications | 2 - Booking core | Confirmation email - exactly once, only on confirmation | System | Appointment becomes confirmed (CUS-03, APT-02) | 1. After the confirming transaction commits, send: date/time, location + map, barber name + phone, services, total, fee paid, due at the shop, 'call your barber to reschedule or cancel'. 2. Set confirmation_sent_at. 3. 'Resend confirmation' button for the barber / owner. | appointments | NEVER sent for a hold. confirmation_sent_at stops a second email when the QPay callback and the sweep both confirm. A failed send is logged and never undoes the confirmation; the resend button covers it. | FND-01 | To do

## Features
# | Requirement | What we decided | Covered by flows | Status | Notes
1 | Multiple locations; any barber can work at any location | Barbers plan shifts per location; nothing ties a barber to one branch. | OWN-01, SHF-01 | To do
2 | Barbers define their own services | Name (EN required, MN optional), price, duration and location are all the barber's call. Same service at another branch = another row with its own price. | BAR-02, BAR-03 | To do
3 | Several services in one appointment | One barber, one location, many lines; total and duration are summed. | CUS-01, APT-04 | To do
4 | Cleanup buffer per barber | Set by the barber, frozen onto each booking. | BAR-01, SHF-04 | To do
5 | Booking fee per barber | Set by the barber, paid online, subtracted from the total at the shop, never refunded. Fee 0 = phone booking only. | BAR-01, CUS-03, APT-07 | To do
6 | Arbitrary shifts, set by the barber | Any days and hours; online booking only inside them. | SHF-01, SHF-02, SHF-03 | To do
7 | Inside-shift bookings use slots; overtime bookings don't | Availability is computed live from shifts minus appointments, so this is automatic. | SHF-04, APT-02 | To do
8 | Bookings are confirmed ONLY by a paid fee or by the barber | Online: only a paid fee confirms. Barber-entered: entering it is the confirmation. The database refuses a confirmed status without confirmed_at. | CUS-03, APT-02, FND-01 | To do
9 | Nothing a customer submits is kept unless money arrives | Before payment only a temporary hold exists; unpaid holds and unpaid QPay in-store orders are deleted. See the Insert audit tab. | CUS-02, CUS-05, STO-02, JOB-01 | To do
10 | Confirmation email only at confirmation, exactly once | Never for a hold; resend button if it fails. | NTF-02 | To do
11 | Phone / in-person bookings with no fee, any time | source = barber, fee 0; creating it is the barber's confirmation, so it's confirmed immediately. Inside or outside shifts. | APT-02 | To do
12 | Reschedule any time, barber only; fee carries over | Same appointment row; history in appointment_events. | APT-03 | To do
13 | Cancel is barber-only; fee kept | Customers call the barber; no online cancel. | APT-05, CUS-06 | To do
14 | No-show keeps the fee | Barber marks it. | APT-06 | To do
15 | Emergency: flag, call list, reschedule each customer | needs_reschedule_at flag + call list with customer contact. | EMG-01, EMG-02 | To do
16 | Customer sees the barber's phone on confirmation | Barber phone is required. | CUS-04, NTF-02 | To do
17 | No double-booking, ever | Database overlap constraint on appointments (and on shifts). | FND-01, CUS-02 | To do
18 | Payments: QPay, cash, POS, bank transfer, split | Must add up to the total exactly before completing. | APT-07, PAY-01, PAY-02 | To do
19 | No tips tracked | Extra money is the barber's; never entered. | APT-07 | To do
20 | Barber login with limited permissions | Same email-OTP login as the owner; scoped to their own data. | FND-02, FND-03 | To do
21 | Barbers sell products at the listed price | In-store order; stock deducted only by the existing settlement path. | STO-01, STO-02 | To do
22 | Commission % per barber (services + products) | Owner-set, versioned; rate frozen on every ledger row. | OWN-03, ACC-01, STO-03, ACC-07 | To do
23 | Cash is owed back to the shop | cash_collected rows; the owner confirms hand-ins. | ACC-01, ACC-04 | To do
24 | POS / transfer / QPay land in the shop's main account | Barber is only credited their share. | ACC-01 | To do
25 | Rent: fixed amount, weekly / 2-weekly / monthly | Agreed by owner and barber; owner confirms payment. | RNT-01, RNT-02, RNT-03 | To do
26 | Rent auto-deducted from payouts | Oldest due charge first, whole charges only. | ACC-05 | To do
27 | Barber earnings and accounting screen | Balance, commission, cash held, rent, payouts. | ACC-02, ACC-03 | To do
28 | Full history of every appointment change | Append-only appointment_events. | APT-03, APT-05, EMG-01 | To do
29 | Price / fee / buffer changes never rewrite bookings | Frozen values on appointments and lines. | BAR-01, BAR-03 | To do
30 | Owner can also be a barber | Admin user linked to a barbers row. | OWN-05 | To do
31 | Booking is purely additive to the shop | Migration 0006 only creates new types and tables; rollback script restores the exact prior schema (verified). | FND-01 | To do

## Schema
Table | Group | Edited by | Purpose | Key columns | Key rules
locations | Core | Owner | Branches. | slug, name_mn/en, address, phone, map_link, is_active | No foreign keys. Deactivate, don't delete.
barbers | Core | Owner; barber edits own profile | People who cut hair. | name, phone (required), bio, photo, booking_fee, buffer_minutes, user_id | user_id optional: a barber can exist without a login.
services | Barber's own | Barber | What a barber offers at one location. | barber_id, location_id, name_en (req), name_mn, price, duration_minutes, is_active | Same service elsewhere = another row. No shared catalog.
barber_shifts | Barber's own | Barber | Planned availability for online booking. | barber_id, location_id, starts_at, ends_at | No overlaps per barber (EXCLUDE). Appointments never reference shifts.
barber_terms | Owner's own | Owner | Commission and rent deal, versioned. | service_cut_bps, product_commission_bps, rent_amount, rent_period, rent_starts_on, effective_from | New row per change; never edited. rent_period: weekly / biweekly / monthly.
rent_charges | Owner's own | System creates; owner confirms | One row per rent due date. | barber_id, amount, due_on, status, paid_via, confirmed_by | Unique (barber, due_on). status: due / paid / waived; paid_via: direct / payout.
appointments | Booking | Barber (customers only via a paid fee) | One visit: barber, location, time, money. A pending row is a temporary hold. | source, starts_at, ends_at, blocked_until, buffer_minutes, status (pending / booked / completed / cancelled / no_show), total, booking_fee, expires_at, confirmed_at, confirmed_by, confirmation_sent_at, needs_reschedule_at, customer name/phone/email | No overlaps per barber on [starts_at, blocked_until) unless cancelled. CHECK: booked/completed/no_show need confirmed_at; online needs booking_fee > 0 and an email. Unpaid holds are deleted, not kept. Barber bookings: fee 0, no hold, confirmed on creation.
appointment_services | Booking | Barber | Lines of an appointment. | service_id, name/price/duration snapshots | Frozen; service edits never change them.
appointment_events | Booking | System | History: created, rescheduled, updated, flagged, cancelled, no_show, completed. | kind, from_starts_at, to_starts_at, actor_id, note | Append-only.
appointment_payments | Booking | Customer (fee), barber (rest) | Fee + balance payments, any method. | kind, method, amount, status, qpay ids, received_by_user_id | Fee paid once; balance may be split. Manual methods are paid on entry. A pending fee row is deleted with its hold.
barber_ledger | Accounting | System + owner | What the shop owes each barber, and vice versa. | kind, gross_amount, rate_bps, amount, appointment_payment_id, payment_id, rent_charge_id | Append-only; balance = sum(amount). Kinds: service_share, product_commission, cash_collected, rent_deduction, payout, settlement, adjustment.
in_store_sales | Booking | Barber | Marks an order as sold in the shop. | order_id (PK), barber_id, location_id | Side table so orders stays untouched.
orders (unchanged) | Shop | - | In-store sales reuse orders. | No column changes. Snapshot address = the shop location; contact_phone = the customer's. | An order is in-store iff it has an in_store_sales row.
payments (unchanged) | Shop | - | Product-sale payments, any method. | No column changes: provider (text) stores qpay / cash / pos / bank_transfer. | Who took it = in_store_sales.barber_id.
users (unchanged) | Shop | Owner | Logins. | No change to user_role. | A user is a barber iff an active barbers row links to them.

## Permissions
Action | Owner | Barber | Customer
Products, prices, stock, settings | Edit | - | -
Locations | Edit | View | View
Barber terms (commission %, rent) | Edit | View own | -
Rent charges: confirm / waive | Yes | View own | -
Payouts, cash hand-ins, adjustments | Yes | View own | -
Own profile, fee, buffer, phone | Edit anyone's | Edit own | -
Services | Edit anyone's | Edit own | View active
Shifts | Edit anyone's | Edit own | -
Book online inside shifts | - | - | Yes
Create booking any time (phone / in person) | Yes | Own only | -
Reschedule / cancel / no-show / complete | Yes | Own only | Call the barber
Emergency flag + call list | Yes | Own only | -
Take payments (QPay / cash / POS / transfer) | Yes | Own appointments & sales | Pays
Sell products in store at listed price | Yes | Yes (recorded as seller) | -
Earnings / ledger | All barbers | Own only | -

## Insert audit
Flow | What gets inserted | Triggered by | Money first? | Verdict | Why
CUS-01 Browse | Nothing | Customer (public) | - | OK | Read only.
CUS-02 Hold the slot | Pending appointment + its lines + pending fee payment | Customer (public) | No (temporary) | Allowed, temporary | The only pre-payment insert. Needed so two people can't pay for one slot. Deleted if unpaid (CUS-05). No events, emails, ledger or attempts log.
CUS-03 Fee paid | Booking confirmed, event, ledger rows | QPay payment | Yes | Behind money | Everything durable about an online booking is written here.
CUS-05 / JOB-01 Sweep | Deletes unpaid holds and unpaid QPay in-store orders | System | - | Cleanup | Unpaid attempts leave no trace.
Removed: online request without a fee | Pending appointment waiting for the barber | Customer (public) | No | REMOVED | A public insert with no money behind it. No-fee barbers are phone-only now; the barber enters those bookings (APT-02).
APT-02 Barber-entered booking | Appointment + lines + event | Barber (logged in) | No | Allowed, on purpose | The barber vouches for a phone / in-person customer. Accountable login, scoped to their own calendar.
APT-03..06, EMG-01/02 | Updates + appointment_events | Barber (logged in) | No | Allowed | Changes to bookings that already exist; events are the audit trail.
APT-07, PAY-01/02 Checkout | Payments + ledger rows | Barber (logged in) | Is the money | Behind money | QPay rows confirm via QPay; cash / POS / transfer rows are the barber's record of money received.
STO-01 Build a sale | Nothing | Barber (logged in) | - | OK | Built on screen only.
STO-02 Take payment | Order + items + payment | Barber (logged in) | Yes (cash/POS/transfer); temporary hold (QPay) | Behind money | Order is written with its first payment. Unpaid QPay hold deleted by the sweep.
OWN-*, BAR-*, SHF-* Setup | Locations, barbers, services, shifts, terms | Owner / barber (logged in) | No | Allowed | Configuration by staff, not customer data; a payment gate makes no sense here.
RNT-02 Rent charges | rent_charges | System | No (it is a bill) | Allowed | Derived from agreed terms; represents money owed, not arbitrary input.
ACC-01, STO-03 Ledger | barber_ledger | System | Yes | Behind money | Written in the same transaction as the paid payment.
ACC-04/05/06 Owner entries | barber_ledger, rent_charges update | Owner (logged in) | Is the money | Behind money | Hand-ins, payouts and corrections are money movements.
NTF-01/02 Emails | Nothing (confirmation_sent_at update) | System | - | OK | -
FND-02 Staff login codes (existing) | otp_codes | Anyone at /admin/login | No | Allowed | Only created for emails that belong to staff; expired codes are cleaned up.
Existing shop checkout (not in these flows) | orders kept as 'expired' when unpaid + a checkout_attempts row per attempt | Customer (public) | No | Breaks the rule today | Open question: apply the same delete-if-unpaid rule to the online shop?